Invitation to Tender

Outcomes Evaluation - Evidencing the Impact of The Lloyds Bank and Bank of Scotland Social Entrepreneurs Programme

- Deadline for receipt of tender proposals: 9am on Monday 5th September 2022

- Anticipated contract start date: Mid-September 2022

- Interviews for shortlisted proposals due to be held w/c 12th September 2022 (provisionally planned for the afternoon of 13th September)

- Work anticipated to have concluded: March/April 2023

- Budget: We are expecting proposals of between £20,000 - £30,000 for this project.

Introduction

The School for Social Entrepreneurs (SSE) is looking to appoint an external consultant(s) to conduct an outcomes evaluation to provide support in exploring and communicating the impact of our flagship national programme, The Lloyds Bank and Bank of Scotland Social Entrepreneurs Programme (LBSEP).

The Lloyds Bank and Bank of Scotland Social Entrepreneurs Programme is run in partnership with the School for Social Entrepreneurs, and jointly funded by The National Lottery Community Fund (The Fund). The programme in Scotland is jointly funded by the Scottish Government.

Launched in 2012, the programme has run for 10 years and is the largest of its kind in the UK. By the end of year 10, the programme will have supported over 2,500 social entrepreneurs to start and grow innovative social organisations across the UK through traditional and Match Trading grants, mentoring and a 12-month action learning programme delivered across SSE.

The School for Social Entrepreneurs

We can’t fix issues like poverty, climate change and ill-health alone. That’s why the School for Social Entrepreneurs exists.

We have helped thousands of people develop the skills, strengths and networks they need to tackle society’s biggest problems. In turn, they help millions of people in need.

We run courses that equip people to start, scale and strengthen organisations that make a positive difference. But we’re not a traditional school. Learning with SSE is inspiring, action-based and accessible. We support people in other ways too, such as funding and mentoring.

Lord Michael Young founded SSE in 1997. Today we work internationally, with teams across the UK, Canada and India.

Together, we’re changing lives and transforming communities.

https://www.the-sse.org/

Firstly, our commitment to inclusion

Diversity is a fact of life. Inclusion is a choice and a practice, for organisations and individuals.  At SSE, our aim is to drive inclusion into every area and activity of what we do: from access to programmes, to grant investment, to board, staff and partnerships.

However you identify, we would like to hear from you in response to this invitation to tender. In our commitment to continue to diversify those we work with, and for this evaluation opportunity in particular, we are especially keen to hear from people from racialised and minoritised communities*, those who identify as LGBTQ+ and those with disabilities.

If you require any reasonable adjustments during this invitation to tender process including assistance with reading of this document, please contact Kylie Dickenson: kylie.dickenson@sse.org.uk  / 0207 089 9120.

Background and context

The Lloyds Bank and Bank of Scotland Social Entrepreneurs Programme

The Lloyds Bank and Bank of Scotland Social Entrepreneurs Programme  is run in partnership with the School for Social Entrepreneurs  and jointly funded by The National Lottery Community Fund. The programme in Scotland is jointly funded by the Scottish Government.

Initially planned over five years (2012-2017), the programme is now in its second five-year phase.

The programme runs an open recruitment process in England and Scotland for a total of 260 places each year and brings together 13 cohorts of approximately 20 students per cohort. Each student receives a grant as part of the 12-month action learning programme delivered across nine regions.

The programme supports social entrepreneurs at different stages of their social enterprise journey to develop the skills, strengths and networks they need to make a positive difference and tackle society’s biggest problems. Each social entrepreneur engages in a comprehensive 12 month learning programme that is inspiring, action based and accessible.

There are three entry levels: Start Up, Trade Up and Scale Up. The learning consists of expert led sessions on topics ranging from business model canvas to measuring social impact, witness sessions (which draw on the practical experiences of entrepreneurs), Action Learning Sets and project visits. The programme also includes a grant and a mentor from the Lloyds Banking Group.

Match Trading Grants

SSE in collaboration with the Lloyds Banking Group and the Fund piloted the first ever Match Trading (MT) cohort during Phase 1 of the programme in 2015-16. This was rolled out, at scale, to all Trade Up and Scale Up level grantees in Phase 2 of the programme. Match Trading is an innovative grant funding initiative that aims to empower social entrepreneurs to develop their trading base by rewarding sales growth through pound-for-pound matches in an increase in income from trading. Instead of giving a fixed amount of grant, an MT grant has capacity to transform the grant funding so that for the first time, grants can directly incentivize trading by ‘matching’ an increase in the organisation’s traded income.

Evaluation Purpose and objectives

Independent evaluations of Phase 1 and of the first half of phase 2 suggested that SSE, Lloyds Banking Group and the Fund delivered a quality programme which developed personal and business skills and economically sustainable and impactful business models. The evaluations explored outcomes and process providing insights for how we could improve programme delivery.

The purpose of this evaluation is to focus on four key themes that we want to explore, do a deep dive into and highlight to a range of audiences. The themes are:

- People & Skills

- Fixing a broken market from within

- Lived Experience

- Policy Insights & Recommendations

The areas we want to explore and evidence within these themes are as follows:

- People & Skills

SSE delivers cohort-based learning to develop the skills and knowledge of social entrepreneurs and third sector leaders.

We want to further evidence how investing in skills development and training for individuals/leaders is an important part of developing a robust and resilient organisation; how building their capacity will enable them to take the organisation forward and achieve greater impact.

We want to understand, evidence, and communicate the scale of people and skills growth achieved over the last 10 years of the programme, and how this has developed organisational resilience and impact, with a particular focus on developing an understanding of the longevity of the programme outcomes (see Appendix B), as well as any other unplanned/unexpected consequences or outcomes, positive or negative.

- Fixing a broken market from within

SSE operates a regional approach to programme delivery by investing in social entrepreneurs in particular locations who aim to make a difference in their chosen area of impact.

We want to take a deep dive into at least one area to understand the difference that 10 years of investment into those communities has made from a social and economic perspective, including local jobs, local commissioning and local spend.

Match Trading is an innovative funding tool that sits alongside other forms of programmatic support. SSE has already gathered some data on the financial performance of grantees receiving Match Trading grants. Our experience and evidence base to date suggests Match Trading grants delivered alongside the action learning do help to reduce grant dependency and increases the trading ratio of social enterprises on the programme thereby building a more solid foundation for a sustainable business model. We’re keen to understand whether there is a difference between the impact of traditional grants and Match Trading grants.

Our aim is to increase our understanding of the return on investment for deploying investment into an area through learning programmes to increase skills and knowledge and grants to support resilience and sustainability.

- Lived Experience

We believe that lived experience, whether primary or secondary, and diversity plays an important part in a person’s motivation and ability to tackle systemic issues of inequality and prejudice.  We want to explore this further and evidence the effect this can have on an individual, their organisation and the communities in which they’re working to help inform future programme delivery. We want to explore the impact of supporting communities from being passive recipients of services to communities igniting change from within.

- Policy Insights & Recommendations

In researching and exploring the above themes of People & Skills, Fixing a broken market from within and Lived Experience, we want to know what the implications are of these findings, how we can use these findings and which key government policies and priorities they link into, on a local, regional and national level.

We’re also keen to ensure that we link these findings into the priorities of the corporate marketplace, as well as Trusts and Foundations, ensuring that we can clearly demonstrate a link between the impact of our learning programmes and the priorities of our stakeholders.

The aim being that we can evidence the overall impact of our approach and take some tangible lessons from the findings to actively turn into service improvements and development opportunities.

Scope

The evaluation will cover 10 years of the programme from 2012 to 2022, using a mix of existing and new consultation data (existing data sources can be found in Appendix A). There are 13 learning cohorts of 20 people across Start Up, Trade Up and Scale Up each year. Programmes have been delivered in the following areas:

| - Cornwall - Dartington - East of England - Hampshire - London | - Midlands - North West - Scotland - Yorkshire & North East |
| --- | --- |

The evaluation will evidence and communicate the impact of the Social Entrepreneurs Programme over the four key themes that we want to explore, also capturing the three main levels of measurement, as per the contracted programme outcomes and SSE’s theory of change:

- For the social entrepreneurs who have participated in the programme

- For their social enterprise, organisation or project

- For the beneficiaries and communities they support

Use of the evaluation findings:

We will use the information generated through this evaluation to:

- Support our continuous learning and strengthen our knowledge base on the longer-term impact and outcomes of the programme.

- Inform our approach, particularly with regard to using Match Trading to incentivise growth and sustainability

- Share key outcomes and learnings with funders, stakeholders, staff, students, Fellows (i.e. social entrepreneurs who have completed the programme)

- Influence how funders allocate money based on impact and return on investment

Methodology

We are looking for an evaluation partner who can work collaboratively with SSE and key stakeholders in a rigorous, innovative and engaging way.

We have already gathered quantitative data to monitor progress towards specified outputs and outcomes and this will be provided to the evaluator(s). This internal data will need to be verified and triangulated (particularly with qualitative data) to understand not only what progress is being made, but also why progress is/is not being made and what lessons we might derive.

Applicants are asked to outline their proposed methodology for meeting the requirements of the evaluation with a focus on the four key themes above. We are interested in applicants’ ideas and are open to proposals using innovative methodologies, appreciating that the final evaluation design will need to be confirmed following agreement of the key evaluation questions. Because SSE approaches learning differently, we welcome those who approach evaluation differently too.

We currently envisage the following, or equivalent, activities being undertaken:

- An in-person inception meeting with key leads within SSE (provisionally planned for 21st September 2022)

- Desk based analysis including review of existing datasets and phase 1 and phase 2 interim evaluations (see Appendix 1)

- Desk based research of local, regional and national economic statistics

- Gather new qualitative feedback using survey or interview questions to supplement our existing data. This could include:

  - Interviews and/or focus groups with representatives of:

    - students, students who are Match Trading recipients, and Fellows

    - Corporate Mentors

    - Senior Management Team

    - Grant Management Team

    - Entrepreneurship Delivery & Support Team

    - Development & External Affairs Team

We anticipate at least some of these activities being undertaken through project visits, with an opportunity to consult with the relevant SSE staff, the social entrepreneur, and some of their beneficiaries.

Areas that we think would enhance the evaluation and are keen to explore and hear your ideas on, include:

- Exploring the potential for a control group to provide comparison between those who attended the programme and those who did not, and those who received traditional grants vs those who received Match Trading Grants.

- Establishing how we can forecast future growth to evidence the impact of an ‘invest to save’ approach to addressing some of societies issues.

Outputs and dissemination

Outputs

We welcome your suggestions on the outputs to be produced. Our current thinking is outlined below.

- Pre-evaluation engagement plan – we would like the evaluation plan to be co-developed through consultations with key staff within SSE to ensure they understand the evaluation and have the opportunity to shape the plan.

- Evaluation plan - confirming key evaluation questions, methodology and timeframes.

- Four theme based draft and final reports – outlining the purpose, methodology and findings of the evaluation in the themes detailed above.  There is no page or word limit for these reports, but consideration should be given to these being engaging and easy to read/digest. These will be provided in word format. The design of the final reports will be managed by SSE.

- Four theme-based evaluation briefings – we would like four theme-based evaluation briefings to be produced which are engagingly written and visually exciting, summarising the main findings from the evaluation. The primary audience for this output will be existing programme partners, prospective partners and funders, and the wider social enterprise sector. We envisage the briefings will be externally focused publications, produced in both print and PDF formats, and include design work such as infographics.

We are interested to hear alternative / additional format suggestions for these ‘briefings’ as you feel appropriate.

Dissemination

We envisage working collaboratively to communicate the headline findings and learnings from the evaluation. We welcome your suggestions on methods for this and as a minimum would like to include programme partners, staff across the network, and trustees in the dissemination phase. We would also like to ideally include prospective partners, the wider social enterprise sector, and students and Fellows. This could be through meetings, events, social media, or other activities and we welcome your suggestions within the proposal.

Timetable, budget and project management

Our timetable for this work is full project completion by 31st March 2023. We envisage the following outline timetable which will be finalised upon commissioning:

- Consultant(s) appointed – Early September 2022

- Inception Meeting – Mid September (provisionally planned for 21st September 2022)

- Pre-evaluation engagement plan developed – early October 2022

- Evaluation Plan developed - Late October 2022

- First draft of each theme-based evaluation report – January 2023

- Final draft of each theme-based evaluation report – February 2023

- Case Studies to be incorporated into reports– February 2023

- Final reports for each theme submitted – March 2023

- Theme-based evaluation briefings – March/April 2023

SSE have a budget of between £20,000 and £30,000 for this evaluation, including VAT.  The budget you submit should include all expenses.

Within SSE, day to day communications and management of the evaluation project will be led by our Entrepreneurship Impact Lead, Sean Gladwin in partnership with the Entrepreneurship Support Lead, Kylie Dickenson.

Your submission

SSE invites organisations interested in tendering for the evaluation to submit a proposal by 9am on Monday 5th September 2022. Proposals should be sent to Sean Gladwin at sean.gladwin@sse.org.uk with “Outcomes Evaluation - Evidencing the Impact of The Lloyds Bank and Bank of Scotland Social Entrepreneurs Programme” in the subject line.

If shortlisted, you may be invited to a virtual meeting to discuss your proposal in more detail.

Your proposal should outline:

- Why you are interested in working with SSE on this project.

- Your proposed methodology and outputs.

- A suggested engagement strategy for the project, focusing in particular on how you plan to involve the students and fellows throughout the UK.

- The team who will deliver the work, including brief CVs and examples of relevant previous contracts team members have undertaken (e.g. evaluation studies, work on social entrepreneurship).

- A breakdown of costs by activity, showing the day rate for each team member. Please indicate if your costs are exclusive/inclusive of VAT (if applicable).

- Any added value you can bring in relation to dissemination of the evaluation outputs.

- An indicative timetable for delivering the key elements of the evaluation (to be finalised through the evaluation plan).

- Details of two referees for work in a similar field you would be happy for us to approach.

Submissions should be no more than 10 pages (excluding appendices) in font size 11.

SSE is committed to undertaking a rigorous independent evaluation of one of its main programmes. However, we are also mindful that our work at SSE and through the social entrepreneurs we support should be creative, inspiring and exciting. Priority will be given to bidders who can effectively combine the dual qualities of rigour and creativity in how this project is delivered and the outputs produced.

If you have any questions whilst preparing your response, please do not hesitate to get in touch with Sean Gladwin on sean.gladwin@sse.org.uk

Appendix A: Existing data sources

The following data sources and information can be made available to the successful provider.

Programme information

- Contractual outputs and outcomes agreed with Lloyds Bank, Bank of Scotland, Scottish Government and the Fund

- Programme structure/content for Start Up, Trade Up and Scale Up courses

- SSE’s Theory of Change

Datasets

- Quantitative data against Programme Outcomes 1-3 (via PowerBI)

- Quantitative data on the financial performance of students on Trade Up and Scale Up programmes including number and value of grants distributed and financial quarterly Match Trading grant reports (via PowerBI)

- Case studies

- Internal evaluation of the Trade Up pilot

Independent evaluation/review

- Phase 1 final evaluation report (summary, full report and learning report)

Summary available here: https://www.the-sse.org/wp-content/uploads/2019/05/SSE-LBGSEP-CLES-UK-phase-one-summary-report.pdf

- Phase 2 Interim evaluation report (summary, full report and learning report)

Summary available here: https://www.the-sse.org/wp-content/uploads/2021/12/SSE-EXECUTIVE-SUMMARY-LandscapeFINAL-VERSION.pdf

Appendix B: Phase 2 programme outcome summary

- Outcome 1: more skilled and confident community leaders

  - Number of social entrepreneurs that demonstrate increased skills and confidence in relation to four key learning outcomes: i) business and entrepreneurial skills, ii) emotional resourcefulness, iii) networks and iv) social impact.

- Outcome 2: more sustainable social enterprises

  - 810 new social entrepreneurs will complete the Start Up course (720 in England) and 70% will still be trading two years later; 360 social entrepreneurs (347 in England) will complete the Trade Up and Scale Up programme and generate at least £2m in new trading income (£1.92m in England) linked to Match Trading.

- Outcome 3: enhanced social impact in communities

  - Each year 234 social entrepreneurs (213 in England) will report on their approach to social impact on completion of the learning programme; participants will increase beneficiaries by an average of 100 people each year; participants will increase volunteers by an average of 6 each year.

We know that language about identity is personal and these terms won’t feel right to everyone. We mean people who may identify as Black, Brown, bi- or multi-racial, being from a diaspora, having Asian/African/Caribbean/Latinx/Middle Eastern/Indigenous heritage, as a "person of colour", Jewish, and/or from a white ethnic minority such as Gypsy, Roma, Traveller. We have consulted our community to shape this language.

By broken markets we mean places or sectors suffering economic decline and low money circulation, and as a result the commercial sector has retreated and the public sector has struggled to cope with rising social problems.